## CR_Weekly
[5 empty] | Pre-Val |  |  |  |  | Validation
NOE-3G IP R100 | 2013-05-01 |  |  |  | 2013-06-01 |  |  |  | 2013-07-01 |  |  |  |  | 2013-08-01 |  |  |  | 2013-09-13 |  |  |  | 2013-10-13 |  |  |  |  | 2013-11-01 |  |  |  | 2013-12-13
| 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
CR estimated per week | 1.232 | 2.079 | 2.387 | 2.387 | 2.387 | 2.387 | 2.772 | 2.772 | 2.926 | 2.926 | 2.926 | 3.311 | 3.311 | 3.311 | 3.157 | 3.157 | 3.157 | 3.157 | 3.08 | 2.926 | 2.695 | 2.618 | 2.618 | 2.618 | 2.618 | 2.618 | 3.234 | 3.234 | 2.772 | 2.387 | 1.848 | 1.848 | 1.617 | 1.54
CR created per week | 1 | 0 | 3 | 0 | 4 | 1 | 6 | 0 | 7 | 5 | 8 | 5 | 6 | 8 | 1 | 2 | 6 | 9 | 1 | 0 | 2 | 0
CR closed per week | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 1 | 8 | 0 | 1 | 0 | 0 | 10 | 0 | 3 | 0 | 12 | 0
CR estimated total | 1.232 | 3.311 | 5.698 | 8.085 | 10.472 | 12.859 | 15.631 | 18.403 | 21.329 | 24.255 | 27.181 | 30.492 | 33.803 | 37.114 | 40.271 | 43.428 | 46.585 | 49.742 | 52.822 | 55.748 | 58.443 | 61.061 | 63.679 | 66.297 | 68.915 | 71.533 | 74.767 | 78.001 | 80.773 | 83.16 | 85.008 | 86.856 | 88.473 | 90.013
CR created total | 1 | 1 | 4 | 4 | 8 | 9 | 15 | 15 | 22 | 27 | 35 | 40 | 46 | 54 | 55 | 57 | 63 | 72 | 73 | 73 | 75 | 75
CR closed total | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 5 | 6 | 14 | 14 | 15 | 15 | 15 | 25 | 25 | 28 | 28 | 40 | 40
CR remained total | 1 | 1 | 4 | 4 | 8 | 9 | 11 | 11 | 18 | 22 | 29 | 26 | 32 | 39 | 40 | 42 | 38 | 47 | 45 | 45 | 35 | 35
4.50.40
4.50.50
4.50.51

## QC_Weekly
[5 empty] | Pre-Val |  |  |  |  | Validation
NOE-3G IP R100 | 2013-05-01 |  |  |  | 2013-06-01 |  |  |  | 2013-07-01 |  |  |  |  | 2013-08-01 |  |  |  | 2013-09-13 |  |  |  | 2013-10-13 |  |  |  |  | 2013-11-01 |  |  |  | 2013-12-01 |  |  |  | 2014-01-01
| 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5
TC estimated per week | 0 | 0 | 0 | 0 | 27.1474 | 50.6751 | 50.6751 | 50.6751 | 50.6751 | 50.6751 | 50.6751 | 54.2947 | 54.2947 | 54.2947 | 54.2947 | 54.2947 | 54.2947 | 50.6751 | 50.6751 | 50.6751 | 50.6751 | 50.6751 | 47.0554 | 45.2456 | 45.2456 | 45.2456 | 45.2456 | 45.2456 | 45.2456 | 36.1965 | 36.1965 | 27.1474 | 27.1474 | 18.0982 | 18.0982 | 18.0982 | 14 | 13
TC executed per week | 0 | 0 | 0 | 0 | 68 | 4 | 48 | 4 | 29 | 58 | 64 | 51 | 104 | 52 | 69 | 35 | 10 | 74 | 59 | -2 | 153 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TC estimated total | 0 | 0 | 0 | 0 | 27.1474 | 77.8224 | 128.4975 | 179.1725 | 229.8476 | 280.5227 | 331.1977 | 385.4924 | 439.7872 | 494.0819 | 548.3766 | 602.6713 | 656.966 | 707.6411 | 758.3161 | 808.9912 | 859.6662 | 910.3413 | 957.3967 | 1002.6423 | 1047.8879 | 1093.1335 | 1138.3791 | 1183.6247 | 1228.8703 | 1265.0668 | 1301.2632 | 1328.4106 | 1355.5579 | 1373.6562
TC executed total | 0 | 0 | 0 | 0 | 68 | 72 | 120 | 124 | 153 | 211 | 275 | 326 | 430 | 482 | 551 | 586 | 596 | 670 | 729 | 727 | 880 | 882
TC remained total | 1437 | 1437 | 1437 | 1437 | 1369 | 1365 | 1317 | 1313 | 1284 | 1226 | 1162 | 1111 | 1007 | 955 | 886 | 851 | 841 | 767 | 708 | 710 | 557 | 555
Note on B4: Author: P0B1 was delayed 4 weeks.

## CR_PivotTable
Count of id | Serverity
Row Labels | 3_major | 4_minor | 2_critic | Grand Total
CR_Closed | 12 | 27 | 1 | 40
CR_InAnalysis | 14 | 7 |  | 21
CR_InTreatment | 3 | 11 |  | 14
Grand Total | 29 | 45 | 1 | 75

## CQ_db
id | headline | severity | State | howFound | prodVer.productVersion_name | submitter | submittedOn | closedOn | closeReason | Submit_Week | Close_Week |  | AP
crms00435536 | [NOE-3G]MiniKB(QWERTY) switch to AZERTY/QWERTZ/NORDIC by "charmap", some characters output error with alt+shift pressed. | 3_major | CR_Closed | internTestAuto | 4.50.00 | hcarina | 2013-05-09 15:19 | 2013-06-21 14:51 | fixed | 19 | 25
crms00437051 | [NOE-3G]Embedded command "keeptalk" response unknown/unregistered command. | 4_minor | CR_Closed | internTestAuto | 4.50.10 | hcarina | 2013-05-21 12:50 | 2013-06-21 15:04 | fixed | 21 | 25
crms00437052 | [NOE-3G]In automation test(telephony,audio,noesip...), terminal sometimes will "connection lost" and reset,details see logs in attachment. | 4_minor | CR_Closed | internTestAuto | 4.50.10 | hcarina | 2013-05-21 12:56 | 2013-06-21 15:06 | fixed | 21 | 25
crms00437056 | [NOE-3G]IP Phone 8068 sometimes audio abnormal and status is not active during conversation | 3_major | CR_Closed | internTestAuto | 4.50.10 | hcarina | 2013-05-21 13:43 | 2013-09-09 17:30 | fixed | 21 | 37
crms00439489 | [NOE-3G R100]8068 cpuload issue:cupload up to 100% when press navigation pad left key and right key several times | 3_major | CR_InAnalysis | valFuncManual | 4.50.20 | janebj | 2013-06-03 10:57 |  |  | 23 | 0 | known performance restriction. To check whether it exists NOE2G EE sets | Jack JIANG
crms00439513 | [NOE-3G R100] 80x8 audio quality is not acceptable compared with NOE 40x8 handsets. | 3_major | CR_InAnalysis | valFuncManual | 4.50.20 | chenchxi | 2013-06-03 14:26 |  |  | 23 | 0 | HW audio tunning issue. Need to discuss with HW team | James ZHANG
crms00439935 | [NOE-3G R100] 8068 netlog to remote TFTP server begin with Step3 but not from step1, 8028/8038 is OK. | 3_major | CR_InAnalysis | internTestAuto | 4.50.20 | hcarina | 2013-06-05 10:33 |  |  | 23 | 0 | TBC with INT | Bignwei LI
crms00439937 | [NOE-3G R100] 8068 will reset repeatly if always press keys before LCD light up. | 3_major | CR_Closed | internTestManual | 4.50.20 | hcarina | 2013-06-05 10:52 | 2013-06-21 15:22 | fixed | 23 | 25
crms00441667 | [NOE-3G R100]cpuload issue:phone initialize at 'connected', cpuload 100% | 4_minor | CR_InAnalysis | valFuncManual | 4.50.20 | janebj | 2013-06-14 12:29 |  |  | 24 | 0 | To check whether it can be optimized | Jiwei MA
crms00441941 | [NOE-3G R100]8068 will reset when ringing mode on by loudspeaker in max volume after adjust volume level to max by automation test case. | 3_major | CR_Closed | internTestAuto | 4.50.30 | hcarina | 2013-06-17 14:08 | 2013-09-09 10:36 | HWreplacement | 25 | 37
crms00441942 | [NOE-3G R100] Voice Quality issue: heavy background noise in both RJ9 and Jack Headset. | 4_minor | CR_InAnalysis | valFuncManual | 4.50.20 | chenchxi | 2013-06-17 14:15 |  |  | 25 | 0 | HW issue. To be tested on P1 | James ZHANG
crms00441974 | [NOE-3G R100] Enquiry call issue:phone press 'Enquiry off' , the call released but phone screen display wrong | 3_major | CR_InAnalysis | valFuncManual | 4.50.20 | janebj | 2013-06-17 15:45 |  |  | 25 | 0 | TBC | Jiwei MA
crms00442406 | [NOE-3G R100]8038 hardware reset during recalling | 3_major | CR_Closed | valFuncManual | 4.50.20 | janebj | 2013-06-19 14:55 | 2013-09-25 17:31 | HWreplacement | 25 | 39 | HW related issue. To be closed. | Jack JIANG
crms00442653 | [NOE-3G R100] 8028 network connect lost suddenly | 3_major | CR_InAnalysis | valFuncManual | 4.50.20 | jackji | 2013-06-20 15:35 |  |  | 25 | 0 | HW PHY stability. | James ZHANG
crms00442659 | [NOE-3G R100] NOE-3G IP phones will not startup when plug in a power adapter or POE. | 4_minor | CR_Closed | valFuncManual | 4.50.20 | ysyang | 2013-06-20 16:07 | 2013-09-25 15:55 | HWreplacement | 25 | 39 | To be closed. HW Power issue | Jack JIANG
crms00444985 | [NOE-3G R100]80x8 will reset,when changing the pc port parameter on OXE | 3_major | CR_InAnalysis | valFuncManual | 4.50.30 | jackji | 2013-07-03 10:06 |  |  | 27 | 0 | To be tested on K1 platform | Jack JIANG
crms00444986 | [NOE-3G R100]:External Mini-Keyboard's actual country code turns to 'azerty' after changed IME | 3_major | CR_Closed | valFuncManual | 4.50.30 | yuanyazh | 2013-07-03 10:33 | 2013-07-23 11:14 | fixed | 27 | 30
crms00444990 | [NOE-3G R100] During MMI window setting port mirror enable,but don't judge whether the PC port security is active | 4_minor | CR_Closed | valFuncManual | 4.50.30 | jackji | 2013-07-03 11:53 | 2013-07-23 09:34 | fixed | 27 | 30
crms00445017 | [NOE-3G R100] In MMI window enable pc port mirror,phone automatic reset.enter MMI window again display mirror PC port disable. | 4_minor | CR_InAnalysis | valFuncManual | 4.50.30 | jackji | 2013-07-03 15:27 |  |  | 27 | 0 | To be checked with TS. Acceptable? | James ZHANG
crms00445212 | [NOE-3G R100]some 80x8 phone connect AOMEL will hardware reset | 4_minor | CR_Closed | valFuncManual | 4.50.30 | janebj | 2013-07-04 14:17 | 2013-09-25 15:57 | HWreplacement | 27 | 39 | To be closed. HW Power issue | Jack JIANG
crms00445301 | [NOE3G-R100]80x8 can not detect AOM10/40/AOMEL "aom_uart test" | 4_minor | CR_Closed | internTestManual | 4.50.30 | hcarina | 2013-07-04 17:11 | 2013-07-23 09:44 | notTakenIntoAccount | 27 | 30
crms00445517 | NOE-3G IP (BCD) : wrong hardware version in the message Unsolicited Hard/Software reset | 3_major | CR_Closed | internTestManual | 4.50.30 | djimli1 | 2013-07-05 16:45 | 2013-07-10 16:43 | wrongConfig | 27 | 28
crms00445657 | [NOE3G-R100]AOMEL sometimes freeze after some operation, It will work normal after replug in. | 4_minor | CR_Closed | internTestAuto | 4.50.30 | hcarina | 2013-07-08 09:23 | 2013-08-30 15:18 | notAproblem | 28 | 35
crms00445836 | [NOE-3G R100]Enter MMI, press 'Port Mirror' item terminal will reset on full OXE. | 3_major | CR_Closed | valFuncManual | 4.50.30 | janebj | 2013-07-09 14:08 | 2013-07-23 09:44 | fixed | 28 | 30
crms00445860 | [NOE-3G TDM] [AOM][OXE]Key press on AOM10 has no any response and looks like broken until reset phone | 4_minor | CR_Closed | valNonRegression | 4.50.51 | pbzeng | 2013-07-09 16:10 | 2013-09-25 12:05 | notTakenIntoAccount | 28 | 39 | NOE2G has the same issue. Not taken into account. | James ZHANG
crms00446259 | [NOE-3G R100]:Phone resets when receive lldp packet generated by NOE 2G phones | 3_major | CR_Closed | valFuncManual | 4.50.30 | yuanyazh | 2013-07-11 14:01 | 2013-08-30 15:17 | fixed | 28 | 35
crms00446310 | [NOE-3G R100]:the connection lost message do not disappear when the connection recover in low probability | 4_minor | CR_Closed | valFuncManual | 4.50.30 | yuanyazh | 2013-07-11 16:26 | 2013-07-26 10:14 | fixed | 28 | 30
crms00446716 | [NOE-3G R100]:Phone resets when received lldp message even in idle state | 4_minor | CR_InTreatment | valFuncManual | 4.50.30 | yuanyazh | 2013-07-15 11:16 |  |  | 29 | 0 | Merge SIP code. 3.00.30? | Jiwei MA
crms00446770 | [NOE-3G R100]: Terminal freezed when input "reset" command in CLI. | 4_minor | CR_InAnalysis | valFuncManual | 4.50.30 | chenchxi | 2013-07-15 16:11 |  |  | 29 | 0 | To check. | Jiwei MA
crms00446786 | [NOE-3G R100]:Phone can not get SIP SUR parameter form call server | 3_major | CR_Closed | valFuncManual | 4.50.30 | yuanyazh | 2013-07-15 16:43 | 2013-07-17 10:41 | notTakenIntoAccount | 29 | 29
crms00446988 | [NOE-3G R100]:Subnet mask should not be saved as 255.255.255.255 in MMI. | 4_minor | CR_Closed | valFuncManual | 4.50.30 | yuanyazh | 2013-07-16 16:14 | 2013-07-23 11:38 | fixed | 29 | 30
crms00447012 | [NOE3G R100] Terminal reset when n=600+ by "defence n" command | 4_minor | CR_Closed | internTestManual | 4.50.30 | hcarina | 2013-07-16 17:09 | 2013-07-23 11:08 | fixed | 29 | 30
crms00447457 | [NOE-3G TDM] [AOM][OXO]Link AOM10 to 80x9 , OMC show AOM10 as AOM40 , and the AOM10 key serial number are disorderly . | 4_minor | CR_InTreatment | valNonRegression | 4.50.51 | pbzeng | 2013-07-18 16:36 |  |  | 29 | 0 | the same as crms00445860
crms00447696 | OXE K1: NOE 3G IP : 80x8 binary is not downloaded on terminals | 2_critic | CR_Closed | valFuncManual | 4.50.30 | dimplers | 2013-07-19 14:41 | 2013-07-23 20:37 | notAproblem | 29 | 30
crms00447698 | [NOE-3G R100] NOE-3G 8038 network connection lost suddenly. config parameter "use VLAN" auto be enabled by phone | 3_major | CR_InAnalysis | valFuncManual | 4.50.30 | jackji | 2013-07-19 14:43 |  |  | 29 | 0 | To reproduce it. | Xiaoguang YAO
crms00448285 | [NOE-3G R100]:the icon for mini-keyboard absence should disappear when we disable this function | 4_minor | CR_Closed | valFuncManual | 4.50.40 | yuanyazh | 2013-07-23 10:27 | 2013-08-30 15:16 | fixed | 30 | 35
crms00448286 | [NOE-3G R100]:Remove the function of icon for mini-keyboard absence from NOE 3G 8028/8038 | 4_minor | CR_Closed | valFuncManual | 4.50.40 | yuanyazh | 2013-07-23 10:51 | 2013-08-30 15:15 | fixed | 30 | 35
crms00448562 | OXE K1: NOE 3G IP: One of the 8068 set goes for reset on specific scenario | 3_major | CR_InAnalysis | valFuncManual | 4.50.30 | dimplers | 2013-07-24 13:26 |  |  | 30 | 0 | HW power supply issue. Fixed in P1 | James ZHANG
crms00449101 | [NOE-3G R100]:ARP SPOOFING: no “arpspoofing start” command can be found in CLI. | 4_minor | CR_Closed | valFuncManual | 4.50.40 | chenchxi | 2013-07-26 09:47 | 2013-09-25 16:48 | obsolete | 30 | 39 | to check with SW External spec. To close. | Jack JIANG
crms00449137 | [NOE-3G R100]:Flash bootloader failed after interrupted the bootloader flashing process at first time | 4_minor | CR_Closed | valFuncManual | 4.50.40 | yuanyazh | 2013-07-26 15:39 | 2013-09-10 17:30 | fixed | 30 | 37
crms00449531 | [NOE-3G R100]:flash customization file causes phone lose soft binary and customization file | 4_minor | CR_Closed | valFuncManual | 4.50.40 | yuanyazh | 2013-07-30 14:23 | 2013-08-30 11:10 | fixed | 31 | 35
crms00449783 | [NOE-3G R100]:embedded command: no "pseudo" option can be used in id command. | 4_minor | CR_Closed | valFuncManual | 4.50.40 | chenchxi | 2013-07-31 14:18 | 2013-08-30 15:14 | fixed | 31 | 35
crms00449907 | OXE K1: NOE 3G IP MODE: 80x8 sets are not getting registered in NOE-SIP mode on SIP TLS node. | 3_major | CR_InAnalysis | valFuncManual | 4.50.30 | dimplers | 2013-07-31 19:21 |  |  | 31 | 0 | Need P1 prototype with Cert. | James ZHANG
crms00450083 | [NOE-3G R100]:Flash language pack failed and phone always reset at step 4. | 4_minor | CR_Closed | valNonRegression | 4.50.40 | ysyang | 2013-08-01 16:18 | 2013-08-30 11:10 | fixed | 31 | 35
crms00450102 | NOE-3G: AOM 40,AOMEL config programmed key 'Forward On Ringing' not available | 3_major | CR_Closed | valFuncManual | 4.50.40 | janebj | 2013-08-01 16:46 | 2013-08-30 15:12 | notAproblem | 31 | 35
crms00450258 | [NOE-3G]AOM issue: phone not reset after connect AOM | 3_major | CR_InTreatment | valFuncManual | 4.50.40 | janebj | 2013-08-02 13:17 |  |  | 31 | 0 | 1. Not taken into account. 2. enhancement. | Xiaoguang YAO
crms00450461 | [NOE-3G R100] AOM not power on in SUR mode | 4_minor | CR_InTreatment | valFuncManual | 4.50.40 | janebj | 2013-08-05 11:01 |  |  | 32 | 0 | 3.00.30 | Xiaoguang YAO
crms00450465 | [NOE-3G R100]AOM10,AOM40 not power on sometimes while AOM module not configured on OXE | 4_minor | CR_InAnalysis | valFuncManual | 4.50.40 | janebj | 2013-08-05 13:06 |  |  | 32 | 0 | try to reproduce with new HW modification. HW to check. | Jack JIANG
crms00450752 | [NOE-3G R100]: Add data info into "binary" command output and add "erase" option to this command to erase l10n, cust, data binaries. | 4_minor | CR_Closed | reqReview | 4.50.50 | bingweil | 2013-08-06 16:38 | 2013-08-30 15:11 | fixed | 32 | 35
crms00450898 | [NOE-3G R100]:MMI:Netlog option status do not display correctly. | 4_minor | CR_Closed | valFuncManual | 4.50.40 | chenchxi | 2013-08-07 10:09 | 2013-09-25 16:20 | obsolete | 32 | 39 | To closed. The same as crms00445017 | Jack JIANG
crms00450933 | [NOE-3G R100]On oxe k1, terminal survival to PCS server, tftp_backup ip change to 255.255.255.255 | 3_major | CR_Closed | valFuncManual | 4.50.40 | janebj | 2013-08-07 15:12 | 2013-08-07 16:45 | wrongConfig | 32 | 32
crms00451345 | [NOE-3G R100]:display no etherent link.when change the speed and duplex mode between phone and switch | 3_major | CR_InAnalysis | valFuncManual | 4.50.40 | jackji | 2013-08-08 16:25 |  |  | 32 | 0 | HW negotiation issue. The same as NOE-2G EE open a ticket to Broadcom | James ZHANG Jiwei MA
crms00451508 | [NOE-3G R100] Connect AOM during phone initialization phase, AOM cannot be detected | 4_minor | CR_Closed | valFuncManual | 4.50.40 | janebj | 2013-08-09 09:31 | 2013-08-30 15:10 | obsolete | 32 | 35
crms00451514 | [NOE-3G R100]With an incoming call ,phone no ringing sound , press some key phone reset | 4_minor | CR_InAnalysis | valFuncManual | 4.50.40 | janebj | 2013-08-09 14:19 |  |  | 32 | 0 | To be checked. | Jiwei MA
crms00452149 | [NOE-3G R100]:Shell popup would not close after 60 seconds without user action on the keyboard | 4_minor | CR_InTreatment | valFuncManual | 4.50.40 | yuanyazh | 2013-08-14 17:12 |  |  | 33 | 0 | to be fixed on 4.50.60 | Jiwei MA
crms00452733 | [NOE-3G R100]on OXO,connect AOM10 to 80x8 , OMC show AOM40 , and the AOM10 programmed keys are disorderly . | 4_minor | CR_Closed | valFuncManual | 4.50.40 | janebj | 2013-08-20 10:16 | 2013-09-23 16:49 | notTakenIntoAccount | 34 | 39
crms00453438 | OXE K1: NOE 3G: Encryption : N\W DSU failed to login over the NOE 3G IP set configured as DSS | 3_major | CR_InAnalysis | valFuncManual | other | dimplers | 2013-08-23 12:57 |  |  | 34 | 0 | Need P1 prototype with Cert. | James ZHANG
crms00453833 | [NOE-3G R100]AOM is unusable sometimes | 4_minor | CR_Closed | valFuncManual | 4.50.50 | janebj | 2013-08-27 10:47 | 2013-09-25 15:58 | notAproblem | 35 | 39 | SATA cable issue. To be closed? | Jack JIANG
crms00454501 | [NOE-3G R100]:8068 lost alcatel-lucent and wind river logo in sip sur initialization UI | 4_minor | CR_InTreatment | valFuncManual | 4.50.50 | yuanyazh | 2013-08-30 10:03 |  |  | 35 | 0 | 3.00.30 | Jiwei MA
crms00454506 | [NOE-3G R100]:Can not light the backlight in SIP SUR mode by pressing any key on 8028 | 3_major | CR_InAnalysis | valFuncManual | 4.50.50 | yuanyazh | 2013-08-30 10:46 |  |  | 35 | 0 | Will be fixed in next SIP version. V3.00.30 | Jiwei MA
crms00454508 | [NOE-3G R100]:8038/8068 displays white ground without any content about 8s before SIP SUR initialization processing | 4_minor | CR_InTreatment | valFuncManual | 4.50.50 | yuanyazh | 2013-08-30 11:10 |  |  | 35 | 0 | 3.00.30 | Jiwei MA
crms00454530 | OXE K1 : NOE 3G IP - Bluetooth is not working in 8068 | 3_major | CR_InAnalysis | valFuncManual | other | dimplers | 2013-08-30 14:26 |  |  | 35 | 0 | Need P1 prototype with Cert. | James ZHANG
crms00454536 | [NOE-3G R100]:Connect to SIP Proxy failed in SIP SUR mode via NOE 3G PC port | 4_minor | CR_InTreatment | valFuncManual | 4.50.50 | yuanyazh | 2013-08-30 14:44 |  |  | 35 | 0 | 3.00.30 | Jiwei MA
crms00454807 | In industrial mode, the BT command does not work without network connection | 4_minor | CR_Closed | externTestManual | 4.50.50 | jiweim | 2013-09-02 09:36 | 2013-09-25 11:35 | fixed | 36 | 39 | 4.50.51 | James ZHANG
crms00454817 | the serial port could not input strings more than 255 bytes. | 4_minor | CR_Closed | externTestManual | 4.50.50 | jiweim | 2013-09-02 10:47 | 2013-09-25 11:49 | fixed | 36 | 39 | 4.50.51 | James ZHANG
crms00454830 | 8028/8038 LCD enhancement | 4_minor | CR_Closed | externTestManual | 4.50.50 | jiweim | 2013-09-02 14:01 | 2013-09-25 11:52 | fixed | 36 | 39 | 4.50.51 | James ZHANG
crms00455045 | [NOE-3G R100]: Dial key could not open the dial panel and take incoming call in SIP SUR mode | 3_major | CR_InTreatment | valFuncManual | 4.50.51 | yuanyazh | 2013-09-03 13:56 |  |  | 36 | 0 | Will be fixed in next SIP version. V3.00.30 | Jiwei MA
crms00455050 | [NOE-3G R100]: Directory could not save the new contacts in SIP SUR mode | 3_major | CR_InTreatment | valFuncManual | 4.50.51 | yuanyazh | 2013-09-03 14:21 |  |  | 36 | 0 | Will be fixed in next SIP version. V3.00.30 | Jiwei MA
crms00455397 | [NOE-3G R100]AOMEL: change AOMEL contrast value issue | 4_minor | CR_InTreatment | valFuncManual | 4.50.51 | janebj | 2013-09-05 10:27 |  |  | 36 | 0 | reset contrast to AOMEL when timeout? | Xiaoguang YAO
crms00455398 | [NOE-3G R100] Change AOMEL contrast value between 5-10, cannot see the change | 4_minor | CR_Closed | valFuncManual | 4.50.51 | janebj | 2013-09-05 11:02 | 2013-09-25 16:25 | fixed | 36 | 39 | fixed on v4.7 | Jack JIANG
crms00455608 | [NOE-3G R100] AOMEL+AOMEL+AOMEL cascade, phone hard reset | 4_minor | CR_InTreatment | valFuncManual | 4.50.51 | janebj | 2013-09-06 09:26 |  |  | 36 | 0 | HW to analysis | James ZHANG
crms00455612 | [NOE-3G R100]AOMEL showed blurred screen somtimes when soft reset | 4_minor | CR_InTreatment | valFuncManual | 4.50.51 | janebj | 2013-09-06 11:07 |  |  | 36 | 0 | fixed on v4.7 | Jack JIANG
crms00455953 | [NOE-3G R100]AOMEL issue:press programmed key to checked/unchecked forward checkbox continuous, AOMEL will refresh screen | 4_minor | CR_InTreatment | valFuncManual | 4.50.51 | janebj | 2013-09-09 16:57 |  |  | 37 | 0 | Not taken into Account. (TBC) | Jack JIANG
crms00458161 | [NOE-3G R100]: 8068 boot failed after continuous reset | 3_major | CR_InAnalysis | valFuncManual | 4.50.51 | yuanyazh | 2013-09-23 15:42 |  |  | 39 | 0 | To open a ticket to Broadcom. | Jiwei MA
crms00458700 | [NOE-3G-TDM][AOMEL]Latin character '?' and '?' on nordic keyboard can't be displayed properly on AOMEL. | 4_minor | CR_InAnalysis | valNonRegression | 4.50.51 | baoxiali | 2013-09-25 15:31 |  |  | 39 | 0
Formulas:
Submit_Week = WEEKNUM([submittedOn])
Close_Week = WEEKNUM([closedOn])

## QC_db
|  | Failed | N/A | No Run | Not Completed | Passed | <Total> |  |  | Test set | Failed | N/A | No Run | Not Completed | Passed | <Total> | Feature Group |  | Failed | N/A | Not Run | Not Completed | Passed | <Total>
| Accessories | 15 | 0 | 0 | 0 | 87 | 102 |  |  | 802.1q DSCP 802.1p |  |  | 2 |  | 18 | 20 | QoS | <unknown> |  | 1 | 91 |  |  | 92
| Audio | 5 | 0 | 13 | 1 | 113 | 132 |  |  | AOM | 6 |  |  |  | 54 | 60 | Accessories | chenchxi | 2 |  |  |  | 160 | 162
| Bluetooth | 0 | 14 | 52 | 0 | 0 | 66 |  |  | appointment |  |  |  |  | 2 | 2 | Serviceability | jackji | 1 |  |  |  | 95 | 96
| Initialization | 10 | 0 | 5 | 1 | 103 | 119 |  |  | ARP spoofing |  |  |  |  | 6 | 6 | Security | janebj | 23 | 1 |  | 1 | 313 | 338
| Download | 5 | 0 | 1 | 0 | 13 | 19 |  |  | audio codec |  |  | 2 |  | 34 | 36 | Audio | ysyang | 5 | 14 |  |  | 136 | 155
| QoS | 0 | 0 | 2 | 0 | 44 | 46 |  |  | audio mode exchange | 5 |  | 10 | 1 | 28 | 44 | Audio | yuanyazh | 19 |  |  | 5 | 128 | 152
| Security | 0 | 0 | 0 | 0 | 57 | 57 |  |  | AVA |  |  |  |  | 19 | 19 | QoS | <Total> | 50 | 16 | 91 | 6 | 832 | 995
| Serviceability | 9 | 0 | 0 | 4 | 92 | 105 |  |  | beep |  |  |  |  | 19 | 19 | Audio
| Telephony | 4 | 2 | 1 | 0 | 125 | 132 |  |  | bootloader perturbation | 2 |  |  |  | 1 | 3 | Download
| Common | 2 | 0 | 17 | 0 | 198 | 217 |  |  | Broker call |  |  |  |  | 9 | 9 | Telephony
| TOTAL | 50 | 16 | 91 | 6 | 832 | 995 |  |  | call back |  |  |  |  | 4 | 4 | Telephony
[10 empty] | call forward |  |  |  |  | 8 | 8 | Telephony
|  | Test Cases Status | [5 empty] | Execution Status |  | Call hold |  |  |  |  | 6 | 6 | Telephony
|  | Failed | N/A | No Run | Not Completed | Passed | <Total> | WEEKLY | TOTAL | call log |  | 1 | 1 |  | 4 | 6 | Telephony
W1313 | 2013/3/24~2013/3/30 |  |  | 206 |  |  | 206 | 0 | 0 | call park |  |  |  |  | 3 | 3 | Telephony
W1314 | 2013/3/31~2013/4/6 |  |  | 246 |  |  | 246 | 0 | 0 | call transfer |  |  |  |  | 9 | 9 | Telephony
W1315 | 2013/4/7~2013/4/13 |  |  | 452 |  |  | 452 | 0 | 0 | Code & Data binaries |  |  |  |  | 8 | 8 | Download
W1316 | 2013/4/14~2013/4/20 |  |  | 529 |  |  | 529 | 0 | 0 | commands | 3 |  |  |  | 15 | 18 | Serviceability
W1317 | 2013/4/21~2013/4/27 |  |  | 572 |  |  | 572 | 0 | 0 | customization binary | 1 |  |  |  | 2 | 3 | Download
W1318 | 2013/4/28~2013/5/4 |  |  | 572 |  |  | 572 | 0 | 0 | deny download |  |  |  |  | 1 | 1 | Download
W1319 | 2013/5/5~2013/5/11 |  |  | 572 |  |  | 572 | 0 | 0 | DHCP |  |  |  |  | 27 | 27 | Initialization
W1320 | 2013/5/12~2013/5/18 |  |  | 698 |  |  | 698 | 0 | 0 | display call duration | 2 |  |  |  | 1 | 3 | Telephony
W1321 | 2013/5/19~2013/5/25 |  | 14 | 753 |  |  | 767 | 0 | 0 | DoS protection |  |  |  |  | 20 | 20 | Security
W1322 | 2013/5/26~2013/6/1 |  | 14 | 753 |  |  | 767 | 0 | 0 | DTMF |  |  |  |  | 4 | 4 | Telephony
W1323 | 2013/6/2~2013/6/8 |  | 14 | 684 | 1 | 68 | 767 | 68 | 68 | Enquiry call |  |  |  |  | 6 | 6 | Telephony
W1324 | 2013/6/9~2013/6/15 |  | 14 | 680 | 1 | 72 | 767 | 4 | 72 | failure signaling |  |  |  |  | 3 | 3 | Serviceability
W1325 | 2013/6/16~2013/6/22 | 3 | 15 | 631 | 1 | 117 | 767 | 48 | 120 | IME | 3 |  |  |  | 13 | 16 | Serviceability
W1326 | 2013/6/23~2013/6/29 | 3 | 15 | 627 | 1 | 121 | 767 | 4 | 124 | input methods |  |  |  |  | 8 | 8 | Serviceability
W1327 | 2013/6/30~2013/7/6 | 7 | 15 | 597 | 2 | 146 | 767 | 29 | 153 | Inter_Release_Compatibility | 1 |  | 1 |  | 1 | 3 | Download
W1328 | 2013/7/7~2013/7/13 | 13 | 16 | 677 |  | 198 | 904 | 58 | 211 | Intrusion |  |  |  |  | 3 | 3 | Telephony
W1329 | 2013/7/14~2013/7/20 | 17 | 19 | 610 |  | 258 | 904 | 64 | 275 | IP sets BTH. |  | 14 | 52 |  |  | 66 | Bluetooth
W1330 | 2013/7/21~2013/7/27 | 18 | 19 | 555 | 4 | 308 | 904 | 51 | 326 | LLDP | 2 |  |  |  | 7 | 9 | Initialization
W1331 | 2013/7/28~2013/8/3 | 26 | 16 | 453 | 5 | 404 | 904 | 104 | 430 | Local MMI | 1 |  |  |  | 25 | 26 | Initialization
W1332 | 2013/8/4~2013/8/10 | 32 | 16 | 398 | 8 | 450 | 904 | 52 | 482 | localization binary | 1 |  |  |  | 2 | 3 | Initialization
W1333 | 2013/8/11~2013/8/17 | 36 | 16 | 329 | 8 | 515 | 904 | 69 | 551 | lock |  |  |  |  | 4 | 4 | Telephony
W1334 | 2013/8/18~2013/8/24 | 45 | 16 | 297 | 5 | 541 | 904 | 35 | 586 | Make call | 2 |  |  |  | 9 | 11 | Telephony
W1335 | 2013/8/25~2013/8/31 | 45 | 16 | 287 | 5 | 551 | 904 | 10 | 596 | MD5 TLS |  |  | 5 | 1 | 26 | 32 | Initialization
W1336 | 2013/9/1~2013/9/7 | 46 | 16 | 217 | 1 | 624 | 904 | 74 | 670 | message & voice mail |  | 1 |  |  | 26 | 27 | Telephony
W1337 | 2013/9/8~2013/9/14 | 46 | 16 | 249 | 1 | 683 | 995 | 59 | 729 | Mini Keyboard | 9 |  |  |  | 33 | 42 | Accessories
W1338 | 2013/9/15~2013/9/21 | 46 | 16 | 247 | 5 | 681 | 995 | -2 | 727 | MMI language | 1 |  |  |  | 1 | 2 | Serviceability
W1339 | 2013/9/22~2013/9/28 | 50 | 16 | 94 | 5 | 830 | 995 | 153 | 880 | MMI Protection |  |  |  |  | 6 | 6 | Initialization
W1340 | 2013/9/29~2013/9/30 | 50 | 16 | 91 | 6 | 832 | 995 | 2 | 882 | mulitline |  |  |  |  | 6 | 6 | Telephony
W1341 | [9 empty] | netdisturb & smartbit |  |  |  |  | 10 | 10 | Security
W1342 | [9 empty] | NOE_3G_R100_automation_Telephony |  |  | 2 |  | 89 | 91 | Common
[10 empty] | NOE_3G_R100_core_light_NR |  |  | 13 |  | 63 | 76 | Common
[10 empty] | NOE_3G_R100_new feature_Mix | 2 |  | 2 |  | 46 | 50 | Common
[10 empty] | overflow |  |  |  |  | 8 | 8 | Telephony
[10 empty] | password |  |  |  |  | 5 | 5 | Telephony
[10 empty] | Pick up |  |  |  |  | 3 | 3 | Telephony
[10 empty] | QoS tickets |  |  |  |  | 7 | 7 | QoS
[10 empty] | reset |  |  |  |  | 8 | 8 | Serviceability
[10 empty] | SIP binary | 1 |  |  |  |  | 1 | Download
[10 empty] | Spacial redundancy | 3 |  |  |  | 7 | 10 | Initialization
[10 empty] | Starting phase message | 3 |  |  |  | 3 | 6 | Initialization
[10 empty] | Survivability to 3rd party SIP | 2 |  |  |  | 26 | 28 | Serviceability
[10 empty] | Survivability to PCS |  |  |  | 4 | 16 | 20 | Serviceability
[10 empty] | Telnet Activation |  |  |  |  | 8 | 8 | Security
[10 empty] | Thales secure VOIP |  |  |  |  | 13 | 13 | Security
[10 empty] | Three party conference |  |  |  |  | 7 | 7 | Telephony
[10 empty] | tone & ring melody |  |  | 1 |  | 32 | 33 | audio
[10 empty] | <Total> | 50 | 16 | 91 | 6 | 832 | 995
[10 empty] | Test Coverage (Pass + Fail ) / (Total - N/A) | 90.09%
[10 empty] | Pass Ratio Pass / Pass + Fail | 94.33%

## CS_CRs
id | headline | state | system | comment
crms00445848 | [NOE-3G R100]:Phone screen go back to homepage when press combation key 'ctrl+shift+u' of AZERTY keyboard twice in dial by name | CR_InTreatment | OXE | W30, K1.400.16
crms00445823 | [NOE-3G R100]: Terminal resets after redundancy platform switchover about 20 seconds | CR_Closed | OXE | W30, K1.400.14
crms00450044 | [NOE IP-TDM:IME]Associated characters can't be updated automatically after validate one character. | CR_InAnalysis | OXO
crms00451698 | [NOE-3G R100]On OXO, replace AOM40 with AOMEL, only 1-14 keys can be programmed | CR_InAnalysis | OXO
crms00450258 | [NOE-3G]AOM issue: phone not reset after connect AOM |  | OXE
crms00452731 | [NOE-3G R100]AOM10\AOM40 program 'speed dial' key via phone, black block icon dispappear if press 'hook-on' back to idle menu | CR_InAnalysis | OXE
crms00450235 | [NOE-3G R100]:Phone download SIPc file failed in SIP SUR domain | CR_Closed | OXE | TBC
crms00453853 | NOE-3G IP sets cannot download or upgrade binary from OXO system | CR_InTreatment | OXO | 018.001